## Sheet1
Pacman in Unreal Engine 5.3
Lapo Falcone | hours
estimated times consider the fact that I'm not familiar with UE | Estimated | Real | Notes
Studying phase | 3 | 3
Play Pacman | 0.5 | 0.5
Watch pro players play Pacman | 0.5 | 0.5
Research for obscure/less known rules | 2 | 2
General design | 5 | 3
Identify principal entities | 1 | 0.5
Define responsibilities of each entity (in general) | 3 | 2
Define how entities talk to each other | 1 | 0.5
Target: Move Pacman in the maze | 42 | 54.5
Design tile system (specific) | 2 | 1.5 | During the implementation I spent a lot of time to make the tile system more robust, in particular to avoid missing some interactions between a pawn and a tile due to drops in the frame rate. Look at BoardPawnMovementComponent class for details.
Design Pacman and the ghosts (specific) | 2 | 0.5
Design level state object (specific) | 2 | 0.5
Implement tile system | 4 | 13 | I had problems studying the various base classes in UE5, since many of them seemed to fit for a component I had to write. At the end I chose an Actor instead of the Component counterpart, and had to learn about ChildActorComponent, initialization phases, and weird bugs/crashes due to the live coding feature. At the end of the day, after I finally had a functioning system with ChildActorComponents, I found out the right base class to use, and re-implemented everything in a couple of hours.
Implement Pacman | 3 | 4
Implement Pacman controller | 3 | 4
Implement ghosts path finding algorithm | 3 | 2
Implement ghosts target tile acquisition (for each ghost) | 3 | 2
Implement movement component | 3 | 8 | Task added later. The basic component is very simple, but most of the time was required to make sure it works even in bad conditions, such as when the framerate is low and it is possible that some of the triggers on the center of the tiles are missed.
Implement level state object (basic version) | 5 | 4
Testing and debug | 12 | 15
Target: Play a Pacman level | 17 | 17
Extend the design of the level state object (modes, points, fruits) | 2 | 3
Implement ghost mode manager | 4 | 4
Implement point system (multipliers, fruit drops, …) | 6 | 4
Testing and debug | 5 | 6
Target: Progress through levels | 18 | 18
Design global state manager (details) | 3 | 2
Implement global state manager | 8 | 9 | Most of the time was spent understanding the initialization flow of UE5.
Actually create the levels | 2 | 1 | Task added later
Testing and debug | 5 | 6
Target: Basic UI | 13 | 9
General design | 3 | 1
Implement start screen | 3 | 2
Implement pause menu | 2 | 1.5
Implement level HUD | 1 | 1.5
Testing and debug | 4 | 3
Target: Make it pretty | 16 | 23
Change cubes into something resembling Pacman and the ghosts | 2 | 3
Add basic animations (if you find them) | 3 | 4
Maybe add some sound effects | 2 | 1
Add scenery | 4 | 7 | Task added later
Add car movement | 3 | 5 | Task added later
Testing and debug | 2 | 3
Target: make sure the game works | 10 | 5
Test the game on someone else's PCs | 2 | 1 | I only had one other PC
Solve problems | 8 | 4
TOTAL | 124 | 132.5
| 16 days | 17 days
12 hours added later during development